## Cover Page
AIRLINE MANAGEMENT SYSTEM
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | L P PRASANTH SAI | Suman Saha
| Role | Team Member
| Signature | Prasanth Sai
| Date | 27/04/2021
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog AIRLINE MANAGEMENT SYSTEM Project ID: INTADM21AJ016/POD3 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points | Work Assigned to
1 | Login Page | Customer/Admin | As a new customer/admin,I should be able to login using my account. | 1) When the url is entered, it should be redirected to login page. 2) Registered users can login using their credentials. 3) Credentials include Username, Password. 4) On clicking on login button,credentials validation is required. 4) If the credentials are validated,then user should be redirected to their dashboard. 5) New users should be redirected to the registration page on clicking on signup button. | 1 | 2 |  | 2021-06-10 | 2021-06-11 | 2 | M.Sri Prapurna (911333)
2 | Customer Registration | Customer | As a new customer, I should be able to register to the application. | 1) When the "Signup" button in the login page is clicked, the URL should be redirected to registration page. 2) Customer should enter all the mandatory fields like name,gmail,phone number,password. 3) After entering all the mandatory details user should be able to click the "Submit" button. 4) If all the mandatory fields are not filled, alert should be raised. 5)After clicking on "Submit" the page should be redirected to the dashboard. | 1 | 2 |  | 2021-06-12 | 2021-06-13 | 2 | M.Sri Prapurna (911333)
3 | Flight Search | Customer | As a customer, I should be able to search for the flights. | 1) A drop down box should be present to select the "from location" and "to location". 2)Date of the journey should be selected. 3)Customer should be able to select the number of passengers travelling. 4) A search button should be available to generate the available flights based on the selected locations if all the required feilds are filled/selected. | 1 | 5 |  | 2021-06-10 | 2021-06-14 | 5 | T.Vishnu Vardhan (911142)
4 | Book a Flight | Customer | As a customer, I should be able to get the flight details based on the locations selected and date of journey. | 1) All the results based on from location and to location should be visible. 2)Customer should be provided with the price of each ticket, available seats and duration of journey. 3)Once customer selected the required flight he/she should be redirected to the payment page. | 1 | 3 |  | 2021-06-10 | 2021-06-12 | 3 | M.Sunil Kumar (911132)
5 | Payment | Customer | As a customer, I should be able to make the required payment. | 1) User should be directed to the payment after confirming the ticket details. 2)The total amount should be visible based on the ticket price of the selected aeroplane and the number of tickets booked. 3) A dropdown box should be availabe to select the mode of payment like credit card, Internet banking etc . | 1 | 3 |  | 2021-06-13 | 2021-06-15 | 3 | M.Sunil Kumar (911132)
6 | My Accounts & settings page | Customer | As a customer, I should be able to see and update my accounts and settings | 1) User can update their name. 2) Have a option to choose their gender. 3) Should be able to choose their DOB. 4) Can see or update their address (city,state) . 5) Should be able to update their mobile number and mail id. | 1 | 5 |  | 2021-06-10 | 2021-06-14 | 5 | Pratik jagtap (911286)
7 | Change Password | Customer | As a customer , I should be able to update my password. | 1) User should have a field to enter a new password. 2) The new password should be confirmed again. 3) The password should be validated. 4)User should be made available with "Change password" button to update the password. | 2 | 1 |  | 2021-06-16 | 2021-06-16 | 1 | Pratik jagtap (911286)
8 | My Bookings | Customer | As a customer, I should be able to view my bookings. | 1) Should be available with customers present bookings coloumn. 2)The present booking includes the scheduled flight details. 3) User should be available with their previous bookings also. 4)The previous bookings include the journey details made by the passenger previously. | 2 | 2 |  | 2021-06-16 | 2021-06-17 | 2 | T.Vishnu Vardhan (911142)
9 | Current Booking | Customer | As a customer, I should be able to view my current bookings. | 1) The upcoming/scheduled travel details should be made available. 2)The travel details include from location,to location, date of journey,scheduled time,mode of payment. | 2 | 2 |  | 2021-06-16 | 2021-06-17 | 2 | M.Sri Prapurna (911333)
10 | Previous Booking | Customer | As a customer, I should be able to view my previous bookings | 1)The previous travel history of the customer should be made available. 2)The travel details include from location,to location, date of journey,scheduled time,mode of payment. | 2 | 2 |  | 2021-06-17 | 2021-06-18 | 2 | Pratik jagtap (911286
11 | Admin login | Admin | As a admin, I should be able to login to the application | 1) When the url is entered, admin should be able to direct to the login page. 2) Login page should consist of username and password. 3) The system should be able to authenticate the admin's user name and password. 4) Alert should be raised if the provided details are incorrect. 5) If the enterd details are valid admin should be directed to his/her dashboard. | 1 | 3 |  | 2021-06-10 | 2021-06-12 | 3 | L.PrasanthSai (911273)
12 | Addition of new flights | Admin | As a admin, I should be able to add new flight operating details. | 1)There should be a option to add new flight details. 2)Flight arrival and departure times should be provided. 3)Flight location must be provided. 4)Flight fare should be defined. 5)I all the required feilds are provided then flight should be added to the services. 6) On successfull addition , the flight details should be visible on the users dashboard. | 2 | 3 |  | 2021-06-16 | 2021-06-18 | 3 | L.PrasanthSai (911273)
13 | Modifying flight operating details | Admin | As a admin, I should be able to modify/delete flight operating details. | 1) Flight arrival and departure times can be modified. 2) Flight locations can be modified. 3)Flight fares can be modified. 4)Current flight details like time can be modified. 5)On successful modification/deletion the details should be visible on dashboard. | 2 | 3 |  | 2021-06-19 | 2021-06-21 | 3 | L.PrasanthSai (911273)
14 | Modifying fleet details | Admin | As a admin,I should beable to add new/modify/delete fleet details. | 1) A option should be provided to add new flights to the airline's fleet. 2)When adding a new flight , flight details should be provided. 3) Admin should be able to modify/delete existing flights in the airline's fleet. | 2 | 3 |  | 2021-06-16 | 2021-06-18 | 3 | M.Sunil Kumar (911132)
15 | Logout | Customer/Admin | As a customer/admin , I wish my session should be ended after selecting logout option | 1) A logout option should be provided so that the user/admin can end their session and all the progress made should be saved before logging off. | 2 | 1 |  | 2021-06-18 | 2021-06-18 | 1 | M.Sri Prapurna (911333)

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000